MINUTES of WP2 SESSIONS DURING KNOWLEDGE SHARING WORKSHOP

Bristol. 4-8 April 2016

Monday 4, afternoon.

Revision of FG and FG-Results from Spain.

Assistants:

WP2: Helena González, Oriol Marimon, Leanne Gunn, David Price, Paul Boniface.

WP3: Mireia Bes, Sam Pollock, Ellie Hart, Kat Wall, Fiona Hyland, Kate Miller, Jon James, Livio Riboli-Sasco, Claire Ribrault

WP4: Isabel Ruiz, Maria Heras, Erick Jensen

WP6: Casimiro Vinzini

Conclusions:

- FG improvement suggestions have been applied to FGs. See Reformulated-FG.

- FG sessions have to be recorded

- FG have to be renamed to Participatory Workshops

- Diversity group from “Consell de Cent” have to be tacked out from analysis.

- Reanalyse subcategories in FG1

- Analyse Low/Medium independently

- Analyse Spain/France/UK independently

- Include students opinions that allows us to extract conclusions

Wednesday Morning

Task 2.2 organization

Assistants:

WP2: Helena González, Oriol Marimon, Leanne Gunn, David Price, Paul Boniface.

WP3: Mireia Bes, Sam Pollock, Ellie Hart, Kat Wall, Fiona Hyland, Kate Miller, Jon James, Livio Riboli-Sasco, Claire Ribrault

WP4: Isabel Ruiz, Maria Heras

WP6: Casimiro Vinzini

Conclusions:

Participatory workshops of Task 2.2 will be implemented following next scheme:

Friday 8, afternoon.

How to include RRI into PERSEIAs

Assistants:

WP2: Helena González, Oriol Marimon, Leanne Gunn, David Price, Paul Boniface, Bérénice Collet, Anissah Benchelah

Conclusions:

- Task 2.1-PERSEIAs can be delivered into 10 to 16 schools until December. In SMS case, they have to delivery before starting Participatory Workshops corresponding to Task 2.2

- Task 2.1-PERSEIAs will be delivered in a Science Festival in case of SMS

- Wendy Sadler from SMS does not be SMS-Responsible Person in UK CS any more. Will be substituted by Reachel in one month or so

- Meriem Fergusson from SMS does not be TRACES-Responsible Person in France CS any more. Will be substituted by Céline and Paul.

- SMS and TRACES will send FG-Data completed before end of May 2016

- All Task 2.1-PERSEIAs will be composed by short sketches

- Each sketch will focus, at least, one RRI topic

- All PERSEIA will have interaction with the public

- During the session, ideas and approximations were shared between the group.