Skype Meeting 14:00 UK time

UOB (Mireia Bes –MB, Kate Miller – KM and Ellie Cripps - EC), SMS (Leanne Gunn – LG, David Price- DP and Bethan Parkes - BP) and Isabel Ruiz Mallen (IRM)

Italics = Agenda Points, Normal = Minutes, Blue = ACTIONS

Manchester schools compromise

- All agreed that leaving the Manchester schools, but providing them with alternative (busking bag/workshop)  and replacing with two Bristol schools is best option. This also solves issues with Albany Academy.

  - DP to contact Manchester schools

  - LG/EC to contact Bristols schools for 2017/8 participatory workshops. Already have Broaklands Academy as medium socio-economic and need another low socio-economic (at least 40% FSM on OFTED website). Have had positive response so should not be an issue.

  - LG to provide IRM with the names of two new schools once confirmed

- Need to provide Manchester schools with alternative (busking bag/workshop) and consider cost of DPs time and travel. Busking bag/workshop not a problem, but need to consider where DP travel money will come from. Possible solution is using SMS from Cardiff to reduce travel, but awaiting more details from Oriol about format of workshops to check feasibility. Will also try and group book schools to reduce travel costs.

  - LG/DP to meet this week to look at SMS budget

  - IRM to confirm if TBVT have travel budget that could be used

  - LG/DP to provide final budget in September once they receive information on workshops from Oriol