## Slide 1
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
Management
Reporting
Report | Elegible period |  | Sent to UOC | UOC sends to EC > Participant portal
First internal (M6) | 01/11/2015 | 30/04/2016 | 20/05/2016 | 
Second internal (M12) | 01/05/2016 | 31/10/2016 | 20/11/2016 | --
INTERIM EC (M15) | 01/11/2015 | 31/01/2017 | 20/02/2017 | 31/03/2017
Third internal (M24) | 01/02/2017 | 31/10/2017 | 20/11/2017 | --
Fourth internal (M30) | 01/11/2017 | 30/04/2018 | 20/05/2018 | --
FINAL EC (M36) | 01/02/2017 | 31/10/2018 | 20/11/2018 | 20/12/18
Notes: Internal as exercises to get familiar with reporting, as well as meeting deadlines, and also to make easier the interim and final reports.
First and second make the interim.
Third and fourth make the final.
After interim approved, second payment.
Participant portal

## Slide 2
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
Management
Reporting
November 2016 | Consortium meeting: reporting clarifications | November, 9-10th | CT
 | Technical report: submission of revised version by partners to WP leaders | November, 11th | All
 | Technical report: submission of revised version by WP leaders to CT | November, 20th | WP leaders
 | Timesheets & financial report: submission by partners to CT | November, 20th | All
December 2016 | Timesheets & financial report: feedback by CT to partners | Ongoing until December, 9th | All
 | Technical report: final version circulated by CT to partners for final check | December, 9th | CT
 | Timesheets & financial report: summary of pm and financial effort circulated by CT to partners | December, 9th | CT
Notes: Timing will be similar for every report.
Thus inputs from WP leaders and partners are important to improve the process.

## Slide 3
EFFORT |  |  |  |  |  |  |  |  |  | 
 | UOC | TBVT | UoB | SMS | UoW | AJA | LAC | UNESCO | EUSCEA | UAB
Effort (Person Months) |  |  |  |  |  |  |  |  |  | 
WP1 | 1,83 | 0 | 0,47 | 0,72 | 0,51 | 0,44 | 0,39 | 0 | 0,05 | 3
WP2 | 0,09 | 1,98 | 0,13 | 2,603 | 0,74 | 0 | 3,12 | 0 | 0 | 0,02
WP3 | 0,47 | 0,2 | 3,08 | 0,62 | 0,57 | 0,74 | 0 | 0 | 0 | 0,5
WP4 | 0,88 | 0,58 | 0 | 0,02 | 1,53 | 0 | 0 | 0 | 0 | 6,71
WP5 | 0 | 0,25 | 0 | 0 | 0 | 0 | 0 | 1,5 | 0 | 0
WP6 | 0,31 | 0 | 0 | 0 | 0,1 | 0,02 | 0 | 0 | 0,75 | 0,22
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total PM | 3,58 | 3,01 | 3,68 | 3,963 | 3,45 | 1,2 | 3,51 | 1,5 | 0,8 | 10,45
 | UOC | TBVT | UoB | SMS | UoW | AJA | LAC | UNESCO | EUSCEA | UAB
Effort Planned |  |  |  |  |  |  |  |  |  | 
WP1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4
WP2 | 2 | 42 | 7 | 30 | 2 | 1 | 18 | 0 | 0 | 2
WP3 | 2 | 4 | 31 | 2 | 6 | 6 | 1 | 0 | 0 | 1
WP4 | 22 | 3 | 0 | 2 | 14 | 1 | 1 | 0 | 0 | 33
WP5 | 2 | 2 | 2 | 1 | 0 | 1 | 2 | 15 | 2 | 1
WP6 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 6 | 18 | 2
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total PM | 42 | 54 | 43 | 38 | 25 | 11 | 24 | 22 | 21 | 43
 | UOC | TBVT | UoB | SMS | UoW | AJA | LAC | UNESCO | EUSCEA | UAB
Effort Planned - Effort executed |  |  |  |  |  |  |  |  |  | 
WP1 | 10,17 | 1 | 0,53 | 0,28 | 0,49 | 0,56 | 0,61 | 1 | 0,95 | 1
WP2 | 1,91 | 40,02 | 6,87 | 27,397 | 1,26 | 1 | 14,88 | 0 | 0 | 1,98
WP3 | 1,53 | 3,8 | 27,92 | 1,38 | 5,43 | 5,26 | 1 | 0 | 0 | 0,5
WP4 | 21,12 | 2,42 | 0 | 1,98 | 12,47 | 1 | 1 | 0 | 0 | 26,29
WP5 | 2 | 1,75 | 2 | 1 | 0 | 1 | 2 | 13,5 | 2 | 1
WP6 | 1,69 | 2 | 2 | 2 | 1,9 | 0,98 | 1 | 6 | 17,25 | 1,78
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total PM | 38,42 | 50,99 | 39,32 | 34,037 | 21,55 | 9,8 | 20,49 | 20,5 | 20,2 | 32,55
Management
Reporting
Notes: Pm effort conservative in some cases. Please be aware that pm must be spent throughout the lifecycle of the project (they can’t be saved, they can’t be surpassed).
Effort filled on timesheets must match the information in the excel FINANCIALTemplate_Interim_Report (and uploaded on the Participant Portal (=Use of Resources)
EVIDENCE!!!

## Slide 4
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
Management
DMP
Pilot on Open Research Data
http://www.zenodo.org, CC license
D1.4: Main elements of data management policy : collection and processing, sharing, preservation
ETHICAL REMARKS
Signed consent forms scanned (intranet) and in paper. TO BE COLLECTED BY UOC AT THE END OF THE PROJECT!
Confidentiality. Anonymization (also non-participants): information kept in CSC computers
Notes: Important to keep consent forms in paper.
Scan them and upload them in the intranet.

## Slide 5
PERSEIAS |  | 
Type of data | Methods | Sample
Primary | Deliberative focus groups | Students from two to four classrooms in each selected school
Primary | Participatory workshops | Students from one classroom in each selected school
IMPACT |  | 
Type of data | Methods | Sample
Secondary | Literature review | Academic articles on science education assessment published at international, peer-reviewed journals
Primary | Participatory workshops | Students from one classroom in each selected school
Primary | Social media analysis | Students’ Twitter contributions
Primary | Individual interviews | Students with Twitter contributions, teachers and early career researchers, and key participants in PERSEIA workshops
Primary | Deliberative focus groups | Students participating in PERSEIAs
Primary | Systematic observation | Students participating in PERSEIAs
Primary | Surveys | Students involved in PERSEIAs and a sample of those who are not participating
Management
DMP
Table 1. Datasets overview
Notes: Check out for collection description for each type of data and method.

## Slide 6
Example of data collection
Focus groups
Will be digitally audio recorded and then copied to an external flash disk. When possible, focus groups will be transcribed in each local language (French, Spanish, and English). During the transcription process references to other persons will be replaced by pseudonyms.
Data will be stored in an Excel database.
Literature review
Data extraction and analysis will be carried out by three coordinated reviewers, according to the keywords and categories of variables previously defined and stored in an Excel database.
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
Management
DMP

## Slide 7
Method | Foreseeable period(s) of collection | Date for deletion | Permanent storage in Open Access?
Deliberative focus groups audio files | November 2015 – March 2017 July 2016 – October 2018 | 5 years after end of project | NO
Deliberative focus groups video files | November 2015 – March 2017 July 2016 – October 2018 | 5 years after end of project | NO
Deliberative focus groups transcripts | November 2015 – March 2017 July 2016 – October 2018 | None | NO
Participatory workshops audio files | November 2015 – July 2016 September 2016 – October 2018 | 5 years after end of project | NO
Participatory workshops transcripts | November 2015 – July 2016 September 2016 – October 2018 | None | NO
Literature review database, keywords and categories | November 2015 – July 2016 | None | YES
Interviews audio files | May 2016 – October 2018 July 2016 – October 2018 | 5 years after end of project | NO
Interviews transcripts | May 2016 – October 2018 July 2016 – October 2018 | None | NO
Survey variables | May 2016 – October 2018 | None | YES
Survey data base | May 2016 – October 2018 | None | NO
Survey IDs and names | May 2016 – October 2018 | 5 years after project ends | NO
DMP
Management
Table 2. Lifecycle of collected data