## Slide 1
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
WP1 Project coordination and management
Main activities conducted
Task 1.1 Project management
Organisation of the kick-off meeting in Barcelona
Advice to partners for management issues and regular communication for technical issues
Contact with the EC project officer
Task 1.2 Facilitation of the consortium communication
Set up and management of the intranet (incl. guidelines)
Elaboration of internal e-newsletter
Task 1.3 Scientific coordination and project monitoring
Elaboration of a Risk Management Plan and a Data Management Plan
Coordination and elaboration of the internal reports
Advisory Board: Roger Strand, Daniel Erice, Emily Dawson, Àgueda Gras, Frank Brunet
Task 1.4 Links to STEM education research projects and networks at European level
Participation in events organised by the NCP and FP7 and H2020 SWAFS projects
Inclusion at the Scientix network

## Slide 2
WP1 Project coordination and management
Main outputs achieved
D1.1 Internal communication strategy and intranet
D1.2 Risk management plan
D1.4 Data management plan
Handbook
First internal e-newsletter
Links to Scientix
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·

## Slide 3
WP1 Project coordination and management
Next activities until Month18
2nd internal e-newsletter (M11-M12)
Coordination and elaboration of the interim report (M15)
Coordination of the review of deliverables and interim report by the AB (milestone M18)
Follow-up of Data Management Plan
Management of the intranet
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·

## Slide 4
WP1 Project coordination and management
Identified challenges
To efficiently manage communication within the consortium (reply all to the consortium email)
To ensure compliance with deadlines in sending required information for reports
To encourage the use of the intranet
To efficiently monitor compliance of DMP and ethical requirements
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·