## Slide 1
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
WP4 Impact assessment
Main activities conducted
Task 4.1 Development of an innovative and participatory impact assessment research methodology
Systematic review of 67 papers on assessment of stem learning/engagement
Exploratory workshop with 10 to 20 students in four selected schools in Spain, four in France and three in the UK
Return of results of exploratory workshops in schools
Refinement of PERFORM’s RRi guidelines
Task 4.2 Evaluation of the social media-based impacts of the performance events on young people’s engagement in science
Social media data collection and preparation of automated analysis tool to evaluate audience responses to performance events.
Task 4.3 Evaluation of the acquisition of transversal competences by students during the educational process
Task 4.4 Assessment of the Responsible Research and Innovation values
Development of an impact assessment strategy and methods

## Slide 2
WP4 Impact assessment
Main outputs achieved
D4.1. Research Report: Methodological aspects of Science Education Assessment
  32 assessment criteria and 93 assessment indicators
  RRi-related science education assessment framework
WP4 Assessment strategy

## Slide 3
WP4 Impact assessment
Next activities until Month18 (UAB & UOC)
Assessment implementation
BEFORE PERSEIAS development
Students: survey pre-PERSEIA (including pilot)
DURING PERSEIAS development
Students: observation PWs
Teachers: strategic informal interviews
AFTER PERSEIAS development
Students: survey post-PERSEIA, focus group
Teachers: formal semi-structured interviews
ECRs: focus group / group interview
Science comm.: group discussion
ECRs: strategic informal interviews
December 2016- January2017
January- March/April 2017
March- May 2017

## Slide 4
WP4 Impact assessment
Next activities until Month18 (UoW)
Ongoing data collection from Twitter and Instagram:
@performstem accounts on Twitter and Instagram in PERSEIAS, and #performstem Hashtag.
Preparing automated analysis tool to process content
Beginning process by preparing categories and having research assistants manually train the analysis tool.
Begin to set up dashboard with automated analysis and storage of social media data available for download and further analysis.

## Slide 5
WP4 Impact assessment
Identified challenges
Establish a calendar to conduct the assessment in each setting (Tasks 4.3, 4.4)
Deal with particularities of each setting to implement the different assesment methods and tools (Tasks 4.3, 4.4)
How to conduct a social media analysis in the UK school where students do not use Twitter? (Task 4.2)
  Set up a scraper tool to gather Instagram posts in addition to Twitter.
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·