## Slide 1
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
WP5 - UNESCO
Main activities conducted
Policy impact and Sustainability Plan of PERFORM
Policy Impact & Sustainability of PERFORM
Sustainability Plan
In order to promote PERFORM and ensure its legacy beyond 2018 UNESCO has participated to a series of meeting and events,
  Washington (May 2016)
    World Bank
    Inter American Development Bank
  ESOF 2016 (July 2016)
MS2 has been uploaded in June on the PP
  Description of the Sustainability Plan
Details

## Slide 2
· PERFORM Consortium Meeting. Paris, November 9th, 2016 ·
WP5 - UNESCO
Next activities until Month18
Deliverable n°5 – Sustainability Plan
        Final draft – 10/01/2017
        Peer review – 3 Weeks (EUSEA)
        Upload on PP – 31/01/2017
Policy Briefs
        UNESCO will start working on the first policy brief (February/march 2017)
1
2
Upcoming Major Events
        Preparation of the Final Meeting with EUSEA
        Preparation of World Science Forum 2017
3