## Slide 1
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP2 Innovative Science Education Methos based in Performing arts
Short description of the work
Task 2.1. Inclusion of the “human dimension” of science and the values embedded in RRI in performance-based activities (led by TBVT)
Task 2.2: Participatory process with young people, teachers and early career researchers (led by TBVT)
Task 2.3. Pilot PERSEIA scaled up into informal context: implementation in science museums (led by TBVT)
Implementation
How
When (timing)
By whom (role of partners)
Challenges

## Slide 2
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP2 Innovative Science Education Methos based in Performing arts
Planned activities (M16-36)
Task 2.1. Inclusion of the “human dimension” of science and the values embedded in RRI in performance-based activities (led by TBVT)
- DELIVERABLE 2.1 IN M16:
Final protocol of tested methods to transform a performance-based activity into a PERSEIA
Adapt the formal document to real users (teachers, SciComms and ECRs).
Dissemination
Implementation
How: Videos, user-friendly guidelines
When (timing): From D2.1 approval to M20 (june)
By whom: TBVT will record videos / generate user-friendly documents/ disseminate in secondary schools in Spain. WP6 for global dissemination.
Challenges: Reach effectively our real audience.

## Slide 3
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP2 Innovative Science Education Methos based in Performing arts
Planned activities (M16-36)
Task 2.2: Participatory process with young people, teachers and early career researchers (led by TBVT)
  First round of Implementation of PW1-6 and delivery of students PERSEIAs
Implementation
How: Spain 4 groups in 2 schools/ UK: 2 groups in 1 school/ France: 4 groups in 2 schools
When (timing) Spain: February (M16)- April (M18)/ UK: February (M16)- April (M18)/ France: February (M16)- May (M19)
By whom: TBVT, SMS, TRACES
Challenges: Effectively deliver 6 PW to conduct a process in which students develop their PERSEIA, following the methodological protocol generated in Task 2.1
  The process cannot be longer than 12h (schools’ requirements)
  Inclusion of ECRs and teachers in a process centred in the student
  Inclusion of different artistic methodologies.

## Slide 4
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP2 Innovative Science Education Methos based in Performing arts
Planned activities (M16-36)
Task 2.2: Participatory process with young people, teachers and early career researchers (led by TBVT)
  Redesign of PW for a second round of implementation
Implementation
How: Spain 4 groups in 2 schools/ UK: 2 groups in 1 school/ France: 4 groups in 2 schools
When (timing) Spain: Before June (M20)/ UK and France: Before Christmas (M26)
By whom: TBVT, SMS, TRACES
Challenges: Effectively deliver 6 PW to conduct a process in which students develop their PERSEIA, following the methodological protocol generated in Task 2.1
  The process cannot be longer than 12h (schools’ requirements)
  Inclusion of ECRs and teachers in a process centred in the student
  Inclusion of different artistic methodologies.

## Slide 5
WP2 Innovative Science Education Methos based in Performing arts
Involvement of the ECR: The ECR felt useless during the workshops and did not brought anything to the pupils.
Involve them in the preparation of the workshops.
Use their personal experience of the ECR as a researcher.
Start the PERSEIA creation from the ECR personal experience and research topic/field. The short time dedicated to choose and think about the questions doesn’t allow the pupils to go further than what they already know and think !
The space for theatre: Impro theatre is collective and takes time, especially for pupils who are discovering it, we can’t rush and risk that they feel insecure, performing something superficial in front of their peers at the end. (SAME TBVT and SMS)
More time must be dedicated to it during the PW : minimum 4 full workshops.
The use of social medias: Didn’t work at all (Same SMS)
  Not allowed to use it at school,
  Need to be very careful with the comments performing teenagers
  No time.
For us, this aspect of the project should be removed.

## Slide 6
WP2 Innovative Science Education Methos based in Performing arts
Short time to prepare the PW
Workshops written by each countries partners in plenty of time (UK.- SMS and UoB).
The space for theatre (we are trying to achive too many things in just 6PW):
Reduce what we are trying to achieve through the PW’s
  Revise everyone’s expectations and find something that is achievable.
The use of social medias:
REMOVED
PERSEIA performance setting.
Let students perform PERSEIA’s at an event in a real busking environment.

## Slide 7
WP2 Innovative Science Education Methos based in Performing arts
Match the requirements of the process in terms of number of students with the reality of schools
Be more flexible with numbers
The space for theatre (we are trying to achive too many things in just 6PW):
Almost no time for rehearsal which made students insecure on stage.
Homework
Need to be removed

## Slide 8
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP2 Innovative Science Education Methos based in Performing arts
Planned activities (M16-36)
Task 2.2: Participatory process with young people, teachers and early career researchers (led by TBVT)
  Second round of implementation following the redesign PW
Implementation
How: Spain 4 groups in 2 schools/ UK: 6 groups in 3 school/ France: 4 groups in 2 schools
When (timing) Spain: October (M24) -December (M26)/ UK and France: January (M27) - May (31)
By whom: TBVT, SMS, TRACES
Challenges: Effectively deliver 6 PW to conduct a process in which students develop their PERSEIA, following the methodological protocol generated in Task 2.1
  Reach all the objectives emerged from the previous PW using a different approach
  Generate DELIVERABLE 2.2: Final protocol of tested methods to generate a transformative participatory educational process by using science and arts-based education approaches

## Slide 9
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP2 Innovative Science Education Methos based in Performing arts
Planned activities (M16-36)
Task 2.3. Pilot PERSEIA scaled up into informal context: implementation in science museums (led by TBVT)
Implementation
How: A knowledge-transfer workshop with the participation of science museum facilitators, will be conducted at a science museum in one of the case studies that will be contacted by TBVT
When (timing): From April (M30) to the end of the project (M36)
By whom: TBVT. Implementation in at least 1 museum n Spain
  CosmoCaixa, Barcelona
  Museo del Cosmos de Tenerife
Challenges: identify science activities implemented in museums and convert them in PERSEIAs
Generate D2.3: Guidelines for PERSEIA adaptation to science-museums