## Slide 1
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP3 Building science education and communication capacity for teachers and early career researchers
Planned activities (M16-36)
Develop and deliver teacher training in France, Spain and UK
Use feedback and evaluation from year 1 to re-develop and deliver year 2 of ECR training
Recruit teachers and researchers to take part in the trainings
Identify scope, focus and form of the toolkits for teachers and ECRs
Design media collection strategy to feed toolkits – arrange for appropriate personnel and briefing in each case study country

## Slide 2
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
Implementation
“Develop and deliver teacher training in France, Spain and UK”
How - Respond to the expressed needs of teachers in each case study country and design training responding to those needs and taking in to account lessons learned on the project.
When (timing) – Spain (training outlined and in process of design – follows the protocol of PERFORM), France (TBC – need update from French, UK (training in development, to be delivered in month 20, recruitment to commence in month 18)
By whom (role of partners) – Spain (TBVT), France (TRACES), UK (UoB)
Challenges – Primarily recruitment. Difficult in all contexts. Spain potentially better placed as this training is featured in the official training programme for teachers at UAB. Particularly challenging in the UK and France. Secondarily, content – no clear techniques arising out of the process of PERFORM that are in a state to be the subject of training in the UK (science busking training already exists, and is well known)
WP3 Building science education and communication capacity for teachers and early career researchers

## Slide 3
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
Implementation
“Use feedback and evaluation from year 1 to re-develop and deliver year 2 of ECR training”
How - Feedback from researchers involved in the process, and observation of training processes and participatory workshops will inform the re-development of the next iteration of training. Additionally, practical insight relating to structure, topics and recruitment from the partners organising the training will inform this process of re-development.
When (timing) – Conversations at the consortium meeting will frame the work going forward. Redevelopment work to begin nominally in month 18, however this may be delayed depending on decisions made about the development of WP2, and how these structures might affect the training needed.
By whom (role of partners) – Spain (UOC, UAB), France (AJA), UK (UoB)
Challenges – (potentially) changing structure of WP2 – unknown effects (similar to yr1 development), recruitment, scheduling
WP3 Building science education and communication capacity for teachers and early career researchers

## Slide 4
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
Implementation
“Identify scope, focus and form of the toolkits for teachers and ECRs”
How - [Scope] somewhat dependent on the outputs of WP2 – still not clear what can and should be communicated. Currently looking for versions of “success” in phase 1. [Focus] Working with colleagues from WP2 and WP3 to identify [Form]Looking at different versions of toolkits and assessing them for application to PERFORM needs.
When (timing) – Planning work to begin in Month 18, but dependent on the redevelopment of the PWs for phase 2, and the outcomes of teacher training, and teacher feedback from phase 1.
By whom (role of partners) – UoB to lead, but with significant input from partners working in each case study
Challenges – At present it is hard to know what can and should be usefully communicated to both teachers and ECRs. It is hoped that feedback and evaluation will help to clarify this.
WP3 Building science education and communication capacity for teachers and early career researchers

## Slide 5
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP3 Building science education and communication capacity for teachers and early career researchers
Implementation
“Design media collection strategy to feed toolkits – arrange for appropriate personnel and briefing in each case study country”
How - Once the scope, form and focus of the toolkits is established, we need to identify the media we will need (photos, videos, interviews etc) in order to plan a collection strategy and brief appropriate persons in each partner country.
When (timing) – will follow on from the toolkit design phase, bulk of this strategy design is intended to happen between Month 20 & 22
By whom (role of partners) – UoB will lead on the strategy design, and then will work with case study partners to identify appropriate personnel to collect media footage, and to brief them correctly.
Challenges – Critical path of dependencies – in order to collect media footage, we will need to know about toolkit content, in order to know this, we will need to know what we are communicating, which all rests on successful evolution of WP2