## Slide 1
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP1 Project coordination and management
Planned activities (M16-36) and implementation
Task 1.1 Project management
Organisation of three SC meetings (Months 24, 30, 36).
Organisation of the PERFORM final general assembly in Paris 2018 (Month 36).
Organisation of the EC review meeting in Barcelona 2017 (Month 18) and another in Month 36 (to be agreed with the EC project officer).
Advice to partners for management issues and regular communication for technical issues.
Update of the project Handbook (e.g, new PERFORM colleagues).
Task 1.2 Facilitation of the consortium communication
Management of the intranet.
Elaboration of two internal e-newsletters (Months 24 and 30). CT will lead and ask partners for inputs.

## Slide 2
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP1 Project coordination and management
Planned activities (M16-36) and implementation
Task 1.3 Scientific coordination and project monitoring
Milestone 3 (Month 18). Use of a specific set of indicators for mid-term evaluation, including RRI. Pending to include answers from TRACES and UoW
Deliverable 1.3. Advisory Board evaluation report (Month 24). CT with the support of WP leaders.
Review of the Data Management Plan (Month 24). All consortium must ensure compliance of data management, especially TBVT and UAB as WP2 and WP4 leaders.
Coordination of third and fourth internal reports (Months 24 and 30), incl. risks updating. CT will lead and coordinate, following a timing strategy. WP leaders will coordinate their WPs. All partners contribute.
Coordination of the EC Final report (Month 36). CT will lead and coordinate, following a timing strategy. WP leaders will coordinate their WP. All partners contribute.
Supervision of ethical requirements: Informed consents !

## Slide 3
· PERFORM Consortium Meeting. Bristol, April 10th, 2017 ·
WP1 Project coordination and management
Planned activities (M16-36) and implementation
(Task 1.3)
Second payment: distribution according to a) participation or b) claimed expenses M1-15 (allowing transfers between partners to cover project’s needs and to support lower budget partners)
Task 1.4 Links to STEM education research projects and networks at European level
Milestone 6. Participation in Scientix networking events and presence of Scientix membres in PERFORM events (Month 30).
Participation in events organised by Scientix partners (e.g., ECSITE 2017)
Participation in events and/or actions organised by the NCP and/or other FP7 and/or H2020 projects.