## Hoja1
|  | 2017 | [8 empty] | 2018
WP | Case study | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 |  | External evaluation meeting | AB contact for reporting |  |  |  | Steering Committee | D1.3 |  | 3rd internal newsletter |  |  |  | Milestone 3 |  | 4th internal newsletter |  |  |  | Final consortium meeting | Final report
|  | Milestone 3 | [5 empty] | 3rd internal report | [5 empty] | 4th internal report
WP2 | Spain | Contact schools (Broggi + Consell) |  | User friendly guidelines from D2.1
|  |  |  | PW redesign |  |  | 15th, first draft of PW | 15-30th, final protocol of PW |  | Milestone 4 | PW implementation |  |  | D2.2 |  | PERSEIA implementation in science museum |  |  |  | D2.3
| France | Last PW of first round |  | Play in 3 schools (task 2.1) | Design of PW | [5 empty] | Second round of PW
PERSEIA Marie Curie
School recruiting
| UK |  |  |  | School gala | [5 empty] | PW1 and PW2 | PW3 and PW4 | Students' PERSEIAs performance | UoB scools visit + WP4 evaluation
PW development
[5 empty] | Meeting with UoB for PW development | Participatory process re-design & participatory process protocol draft (15 Aug-15 Sept)
CSC share first draft of participatory process with consortium (mid-Sept)
WP3 | Spain |  | ECR evaluation work with WP4 in Barcelona (15-17th) |  | Teachers' training |  |  |  | ECR training | [7 empty] | Teachers' training
| France | [5 empty] | Teachers' training start | ECR recruiting | ECR training (28-29) |  |  | Teachers' training |  | Teachers' training end
| UK |  | Toolkit development
[17 empty] | D3.1 |  |  | D3.2
WP4 | Spain | Implementation Assessment Strategy |  | Analysis of results (April - July) | Sharing of results |  |  | Review assessment strategy
|  | Data collection task 4.2. | [5 empty] | Milestone 4
| France | Implementation Assessment Strategy (April- June) |  | Analysis of results | Sharing of results |  |  | Review assessment strategy
Data collection task 4.2.
| UK | Implementation Assessment Strategy |  | Analysis of results | Sharing of results |  |  | Review assessment strategy
Data collection task 4.2. alternative to social media
Focus groups + interviews+ visit UoB
WP5 | [5 empty] | Roundtable meetings with electoral groups of UNESCO MS |  |  | World Science Forum 7th-11th | [7 empty] | ESOF 2018 9th-14th | Policy Briefing 2 |  | Reporting
WP6 |  | Send Fb + Twitter guidelines | Videos for dissemination | [9 empty] | Final version of the programme for final conference | Dissemination of the final conference |  | FINAL CONFERENCE |  |  |  | Reporting
|  | Organisation of final conference | Contact more networks for dissemination purposes | [10 empty] | PSCT 2018
Production and edition of videos
Post facebook, twitter, instagram about the project
Tackling of dissemination done by partners
EC open doors days