## Full1
LIST OF DELIVERABLES in numerical order
Deliverable | Upload to Participant Portal | Author | Send to peer-reviewer before | Peer-review by |  |  | Peer-reviewer sends back before
D1.1 Internal communication strategy and intranet | 2016-02-28 | UOC | 2016-02-07 | EUSEA | UAB | . | 2016-02-14
D1.2 Risk management plan | 2016-04-30 | UOC | 2016-04-09 | UoB | TBVT | . | 2016-04-16
D1.3 Evaluation Report of the Advisory Board | 2017-10-31 | UOC | 2017-10-10 | UNESCO | TRACES | . | 2017-10-17
D1.4 Data Management Plan | 2016-04-30 | UOC | 2016-04-09 | UAB | EUSEA | . | 2017-04-16
D2.1 Final protocol of tested methods to transform a performance-based activity into a PERSEIA | 2017-02-28 | TBVT | 2017-02-07 | UoB | UoW | UOC | 2017-02-14
D2.2 Final protocol of tested methods to generate a transformative participatory educational process by using science and arts-based education approaches | 2018-04-30 | TBVT | 2018-04-09 | UoB | AJA | UOC | 2018-04-16
D2.3 Guidelines for PERSEIA adaptation to science-museums | 2018-10-31 | TBVT | 2018-10-10 | EUSEA | UoW | UOC | 2018-10-17
D3.1 Toolkit for researchers wanting to develop PERSEIAs | 2018-07-31 | UoB | 2018-07-10 | TBVT | AJA | UOC | 2018-07-17
D3.2 Toolkit for teachers wanting to develop PERSEIAs | 2018-10-31 | UoB | 2018-10-10 | SMS | TRACES | UOC | 2018-10-17
D4.1 Research report: Methodological aspects of science education assessment | 2016-05-31 | UAB | 2016-05-10 | TBVT | UoW | UOC | 2016-05-17
D4.2 Report on social media responses to science performances | 2018-09-30 | UoW | 2018-09-09 | SMS | UAB | UOC | 2018-09-16
D4.3 Policy brief: Effective science and arts-based education approach | 2018-10-31 | UAB | 2018-10-10 | UNESCO | AJA | UOC | 2018-10-17
D5.1 Sustainability plan | 2017-01-31 | UNESCO | 2017-01-10 | EUSEA | SMS | UOC | 2017-01-17
D5.2 Two policy briefs on WP5 related topics | 2018-08-31 | UNESCO | 2018-08-10 | UoW | UAB | UOC | 2018-08-17
D6.1 Plan for communication, dissemination and exploitation | 2016-02-28 | EUSEA | 2016-02-07 | UNESCO | AJA | UOC | 2016-02-14
D6.2 Website and social media launch | 2016-04-30 | EUSEA | 2016-04-09 | SMS | LAC | UOC | 2016-04-16
D6.3 Report on outreach activities, including the final conference | 2018-09-30 | EUSEA | 2018-09-09 | UNESCO | TBVT | UOC | 2018-09-16
MILESTONES
MS1 Selection of the specific training skills to be developed | 2016-03-31 | UoB
MS2 Identification of actions for sustainability | 2016-06-30 | UNESCO
MS3 Midterm internal evaluation | 2017-04-30 | UOC
MS4 ICT development of an automated tool to enable social media data analysis | 2017-10-31 | UoW
MS5 Inclusion of the RRI values | 2017-12-31 | TBVT
MS6 Links to Scientix | 2018-04-30 | UOC

## Full2
DEADLINES for each partner
Partner | deliverables | deadline | peer-review | deadline
UOC | D1.1 | 2016-02-07 | D6.1 | 2016-02-14
| D1.2 | 2016-04-09 | D6.2 | 2016-04-16
| D1.4 | 2016-04-09 | D4.1 | 2016-05-17
| MS3 | 2017-04-30 | D5.1 | 2017-01-17
| D1.3 | 2017-10-10 | D2.1 | 2017-02-14
| MS6 | 2018-04-30 | D2.2 | 2018-04-16
|  |  | D3.1 | 2018-07-17
|  |  | D5.2 | 2018-08-17
|  |  | D4.2 | 2018-09-16
|  |  | D6.3 | 2018-09-16
|  |  | D2.3 | 2018-10-17
|  |  | D3.2 | 2018-10-17
|  |  | D4.3 | 2018-10-17
UAB | D4.1 | 2016-05-10 | D1.1 | 2016-02-14
| D4.3 | 2018-10-10 | D1.4 | 2017-04-16
|  |  | D5.2 | 2018-08-17
|  |  | D4.2 | 2018-09-16
TBVT | D2.1 | 2017-02-07 | D1.2 | 2016-04-16
| MS5 | 2017-12-31 | D4.1 | 2016-05-17
| D2.2 | 2018-04-09 | D3.1 | 2018-07-17
| D2.3 | 2018-10-10 | D6.3 | 2018-09-16
UoB | MS1 | 2016-03-31 | D1.2 | 2016-04-16
| D3.1 | 2018-07-10 | D2.1 | 2017-02-14
| D3.2 | 2018-10-10 | D2.2 | 2018-04-16
SMS |  |  | D6.2 | 2016-04-16
|  |  | D5.1 | 2017-01-17
|  |  | D4.2 | 2018-09-16
|  |  | D3.2 | 2018-10-17
UoW | MS4 | 2017-10-31 | D4.1 | 2016-05-17
| D4.2 | 2018-09-09 | D2.1 | 2017-02-14
|  |  | D5.2 | 2018-08-17
|  |  | D2.3 | 2018-10-17
AJA |  |  | D6.1 | 2016-02-14
|  |  | D2.2 | 2018-04-16
|  |  | D3.1 | 2018-07-17
|  |  | D4.3 | 2018-10-17
LAC |  |  | D6.2 | 2016-04-16
|  |  | D1.3 | 2017-10-17
|  |  | D3.2 | 2018-10-17
UNESCO | MS2 | 2016-06-30 | D6.1 | 2016-02-14
| D5.1 | 2017-01-10 | D1.3 | 2017-10-17
| D5.2 | 2018-08-10 | D6.3 | 2018-09-16
|  |  | D4.3 | 2018-10-17
EUSEA | D6.1 | 2016-02-07 | D1.1 | 2016-02-14
| D6.2 | 2016-04-09 | D5.1 | 2017-01-17
| D6.3 | 2018-09-09 | D1.4 | 2017-04-16
|  |  | D2.3 | 2018-10-17

## Full3
DELIVERABLES and MILESTONES in order of deadline
Deliverables and Milestones | Upload to Participant Portal | Author | Send to peer-reviewer before | Peer-review by |  |  | Peer-reviewer sends back before
D1.1 Internal communication strategy and intranet | 2016-02-28 | UOC | 2016-02-07 | EUSEA | UAB | . | 2016-02-14
D6.1 Plan for communication, dissemination and exploitation | 2016-02-28 | EUSEA | 2016-02-07 | UNESCO | AJA | UOC | 2016-02-14
MS1 Selection of the specific training skills to be developed | 2016-03-31 | UoB
D1.2 Risk management plan | 2016-04-30 | UOC | 2016-04-09 | UoB | TBVT | . | 2016-04-16
D1.4 Data Management Plan | 2016-04-30 | UOC | 2016-04-09 | UAB | EUSEA | . | 2017-04-16
D6.2 Website and social media launch | 2016-04-30 | EUSEA | 2016-04-09 | SMS | LAC | UOC | 2016-04-16
D4.1 Research report: Methodological aspects of science education assessment | 2016-05-31 | UAB | 2016-05-10 | TBVT | UoW | UOC | 2016-05-17
Internal Report (M6) |  | ALL | 2016-05-20 |  |  | UOC
MS2 Identification of actions for sustainability | 2016-06-30 | UNESCO
Internal Report (M12) |  | ALL | 2016-11-20 |  |  | UOC
D5.1 Sustainability plan | 2017-01-31 | UNESCO | 2017-01-10 | EUSEA | SMS | UOC | 2017-01-17
D2.1 Final protocol of tested methods to transform a performance-based activity into a PERSEIA | 2017-02-28 | TBVT | 2017-02-07 | UoB | UoW | UOC | 2017-02-14
Intermediate Report (M15) | 2017-03-31 | ALL | 2017-02-20 |  |  | UOC
MS3 Midterm internal evaluation | 2017-04-30 | UOC
D1.3 Evaluation Report of the Advisory Board | 2017-10-31 | UOC | 2017-10-10 | UNESCO | LAC | . | 2017-10-17
MS4 ICT development of an automated tool to enable social media data analysis | 2017-10-31 | UoW
Internal Report (M24) |  | ALL | 2017-11-20 |  |  | UOC
MS5 Inclusion of the RRI values | 2017-12-31 | TBVT
D2.2 Final protocol of tested methods to generate a transformative participatory educational process by using science and arts-based education approaches | 2018-04-30 | TBVT | 2018-04-09 | UoB | AJA | UOC | 2018-04-16
MS6 Links to Scientix | 2018-04-30 | UOC
Internal Report (M30) |  | ALL | 2018-05-20 |  |  | UOC
D3.1 Toolkit for researchers wanting to develop PERSEIAs | 2018-07-31 | UoB | 2018-07-10 | TBVT | AJA | UOC | 2018-07-17
D5.2 Two policy briefs on WP5 related topics | 2018-08-31 | UNESCO | 2018-08-10 | UoW | UAB | UOC | 2018-08-17
D4.2 Report on social media responses to science performances | 2018-09-30 | UoW | 2018-09-09 | SMS | UAB | UOC | 2018-09-16
D6.3 Report on outreach activities, including the final conference | 2018-09-30 | EUSEA | 2018-09-09 | UNESCO | TBVT | UOC | 2018-09-16
D2.3 Guidelines for PERSEIA adaptation to science-museums | 2018-10-31 | TBVT | 2018-10-10 | EUSEA | UoW | UOC | 2018-10-17
D3.2 Toolkit for teachers wanting to develop PERSEIAs | 2018-10-31 | UoB | 2018-10-10 | SMS | LAC | UOC | 2018-10-17
D4.3 Policy brief: Effective science and arts-based education approach | 2018-10-31 | UAB | 2018-10-10 | UNESCO | AJA | UOC | 2018-10-17
Final Report (M36) | 2018-12-20 | ALL | 2018-11-20 |  |  | UOC