PERFORM fourth internal report: M25 (November 2017) –M30 (April 2018)

| April, 2018 | Technical report #4: submission of M25-M30 activities by WP leaders to partners | April, 20th | WP leaders |
| --- | --- | --- | --- |
|  | Communication of dissemination activities partners to CT | April, 27th | All |
| May, 2018 | Timesheets and financial report: Submission of M25-M30 update by partners to CT | May, 4th | All |
|  | Technical report #4: submission of feedback by partners to WP leaders | May, 4th | All |
|  | Technical report #4: final version circulated by WP to CT | May, 20th | WP leaders |
|  | Technical report #4: final version circulated by CT topartners | May, 29th | CT |